## excel
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Comments
| 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | First day of the week
Problem Scoping | [14 empty] | Review to ensure scoping is correct | bar: 2021-07-19
Data Acquisition | [14 empty] | Contact industry connections to arrange access to PitchBook | bar: 2021-07-19 to 2021-07-26
Discovery & Visualisation | [14 empty] | Outlined in research proposal | bar: 2021-07-26
Data Preparation | [14 empty] | Outlined in research proposal | bar: 2021-08-02 to 2021-08-16
Model Selection & Training | [14 empty] | Outlined in research proposal | bar: 2021-08-16 to 2021-08-30
Model Tuning | [14 empty] | Outlined in research proposal | bar: 2021-08-30 to 2021-09-13
Solution Presentation | [14 empty] | Outlined in research proposal (dissertation writing separate) | bar: 2021-09-13 to 2021-09-27
Report Writing | [14 empty] | Make weekly contributions, writing every day as step through methodology | bar: 2021-07-19 to 2021-10-04
Review/Editing | [14 empty] | Review dissertation deliverable between initial and final submission dates | bar: 2021-10-11
Submission (22/10/2021) | [14 empty] | Split into an preliminary submission for feedback (4/10/21), receive from supervisor to edit (11/10/21) and final submission (22/10/21) | bar: 2021-10-04; 2021-10-18
Supervisor meeting | [14 empty] | Meet with supervisor once every two weeks to discuss progress, dissertation problems and resolutions | bar: 2021-07-26; 2021-08-09; 2021-08-23; 2021-09-06; 2021-09-20; 2021-10-04